Next Steps — Path to a Functional NYC Pilot

NYC Streetlight Complaint Hub  ·  Drafted 2026-05-16

For: Nischal Divecha and Mithran Sadasivam

Based on the production-readiness audit. Organized by phase, with owners, effort estimates, and clear "done means" criteria.

The hardest question — read this first

Every technical gap in our audit is solvable in a week or two of code. The bottleneck is institutional, not technical. Without a real agency partner running real dispatches through the tool, every improvement we ship is theater. The single most important next step is not on any technical list — it is securing one specific introduction to one specific person at NYC SBS, MOCS, or a DOT borough operations office, with a commitment to pilot one complaint category through the tool for one quarter.

Everything below is sequenced on the assumption that we will land that partner. If we do not, we should stop building and spend our time on partnership outreach instead.

Phase 1 — Pre-pilot (now → Tue 5/19)

Goal: walk into the Shukla meeting with a tool that is demo-credible AND a specific institutional ask. Bring a working tool but lead with the question.

1a. The Shukla ask (Nischal leads)

☐  Draft one-paragraph "what we want from this meeting" before you walk in. The ask is not "what do you think of this?" The ask is: "Can you introduce us to one person at SBS, MOCS, or a DOT borough office who would pilot one complaint category through this tool for one quarter?"

☐  Print the methodology doc + this next-steps doc + a 1-page summary of the matrix. Hand them over physically. Do not assume he will open email attachments.

☐  Bring laptop with live demo loaded. Internet may not be reliable in the meeting room — pre-cache the site, have screenshots as backup.

☐  Have a specific second ask ready: legal review of the demographic display question. The microgrant explicitly covered legal support. Use that.

1b. PPB 3-08 memo generator (Mithran leads, ~2 days)

The single highest-leverage technical feature we have not built. Without it, even after the matrix picks a vendor, agency staff still face manual paperwork. With it, the loop closes.

☐  Build a server route (Cloudflare Worker) that accepts a vendor_id + complaint_id and returns a filled PDF.

☐  Template fields: vendor formal name, MBE/WBE certification ID, NIGP/NAICS code, dollar amount, work description from complaint, PPB Rule 3-08 citation, responsibility-determination checklist, signature block.

☐  PDF generation via puppeteer or pdfkit (Node) or weasyprint (Python).

☐  Done means: clicking "Submit and dispatch" downloads a PDF the agency staffer could plausibly sign and submit.

1c. Mobile + accessibility polish (Nischal leads, ~1 day)

☐  Audit every section at 375px width on iPhone Safari and Android Chrome viewports.

☐  Vendor card badge row: verify it wraps cleanly, doesn't overflow horizontally.

☐  Equity-impact KPI tiles: single-column stack on mobile.

☐  Run Lighthouse accessibility audit. Fix any color-contrast failures on score chips, badges, and the score-bar fills.

☐  Camera capture: <input type="file" accept="image/*" capture="environment"> on the photo upload field.

☐  Done means: clean rendering on Nischal's phone and Mithran's phone, plus 90+ Lighthouse accessibility score.

1d. Site polish (either, ~half day)

☐  Update favicon to something matching the new equity-first branding.

☐  Add meta description and Open Graph tags so the URL previews cleanly when shared.

☐  Add a "Last updated" timestamp at the page footer pulling from vendors.json generatedAt.

Phase 2 — Pilot prep (5/19 → 6/15)

Goal: stand up the persistence layer + identity + vendor consent so a real agency can actually use the tool against real data.

2a. Pick and stand up the database (joint, ~3-4 days)

Decision deadline: Fri 5/23. Recommendation per HANDOFF.md: Supabase (Postgres + auth + storage + row-level security on the free tier).

☐  Create Supabase project, set up the four required tables: complaints, vendors_snapshot, dispatches, outcomes, audit_log.

☐  Migrate the static vendors.json into a vendors_snapshot table; nightly refresh job repopulates it.

☐  Wire complaint submission to write to complaints table.

☐  Wire vendor selection to write to dispatches table with full score snapshot.

☐  Done means: every action through the UI persists to a real database; nothing is lost on page refresh.

2b. Vendor portal v1 (Mithran leads, ~1 week)

Vendors need to claim their record, verify contact info, and consent to being listed in our directory. Without this, we have legal exposure when an agency dispatches via a vendor record the vendor never registered for.

☐  Build /vendor/claim flow: vendor enters license number, gets magic-link via email/SMS on file with DOB.

☐  Build /vendor/profile page: vendor can update contact info, set service areas, opt out of demographic-badge display, mark themselves available/unavailable.

☐  Build "almost eligible" prompts: a vendor in tier 2 sees "you would be eligible if you enrolled in PASSPort" with a direct link to the SBS PASSPort registration page.

☐  Done means: a vendor can independently find their record, claim it, and update it without our involvement.

2c. Auth via NYC.id for agency staff (Mithran leads, ~3-5 days)

☐  Confirm NYC.id supports third-party SSO (it should — used by other NYC civic-tech tools).

☐  Add role-based access: citizen (no login), dispatcher (NYC.id), vendor (magic link), admin (us).

☐  Every dispatch in the audit_log is attributed to a user ID + timestamp.

☐  Done means: agency staff log in via NYC.id; we know exactly who dispatched what.

2d. Dispatch send mechanism (Nischal leads, ~3 days)

☐  Stand up a transactional email provider (Resend free tier covers our pilot scale).

☐  SPF/DKIM/DMARC records for nyc-streelight.com so emails don't land in spam.

☐  On dispatch: send work order PDF + PPB 3-08 memo to vendor email; CC citizen if they opted in; CC dispatcher.

☐  Done means: a real dispatch actually emails the vendor and produces audit evidence the email was sent.

2e. Legal review (external)

☐  Ask Shukla (via 5/19 meeting outcome) for an E&I Hub legal contact.

☐  Questions to ask: (1) Is publishing demographic badges from ci93-uc8s OK? (2) Can our PPB 3-08 memo be legally relied on, or does the agency lawyer need to draft each one? (3) Citizen data retention requirements?

☐  Done means: written legal opinion in our docs/ folder addressing the three questions.

2f. The pilot agreement (Nischal leads, depends on partner)

☐  Once we have an agency contact (from 1a), draft a one-page pilot memo: scope (1 borough or 1 complaint type), duration (1 quarter), success criteria (≥30 dispatches; ≥50% to M/WBE; ≥80% citizen satisfaction), exit terms.

☐  Done means: signed informal agreement with the partner agency before pilot launch.

Phase 3 — Pilot live (6/15 → 9/15)

Goal: 30+ real dispatches. Real outcome data. Replace theoretical impact numbers with measured ones.

3a. Outcome feedback loop (joint, ongoing)

☐  Post-dispatch SMS to citizen at +30 days: "Did the work get done? Rate 1-5."

☐  Vendor-side completion attestation: vendor confirms in their portal when the job closes.

☐  Both feed back into component 5 (reliability) at runtime, making the score adapt to real performance.

☐  Done means: every dispatch has either a citizen rating, a vendor attestation, or both, within 60 days of dispatch.

3b. Vendor data refresh + alerting (Nischal leads, ~2 days)

☐  Scheduled job (Cloudflare Worker cron or GitHub Actions): refresh vendors.json daily.

☐  Diff against previous snapshot. Log any vendor that fell out of tier 1 eligibility.

☐  Email alert if a vendor we recently dispatched to has lost eligibility (cert expired, license suspended).

☐  Done means: vendors lose tier 1 status within 24 hours of the underlying data change.

3c. Weekly review cadence (joint)

☐  Every Monday 30-min standup: review all dispatches from the previous week, outcomes received, vendors that declined, any complaints from incumbents.

☐  Adjust matrix weights or hard filters based on what we observe.

☐  Document every weight change with a 1-sentence rationale in the commit message.

3d. Quality outcomes report (mid-pilot, week 6)

☐  Pull all dispatches + outcomes. Compare matrix picks vs. counterfactual "what the incumbent would have done."

☐  Specific question to answer: do matrix picks have comparable outcomes to incumbent primes on the same complaint types?

☐  Done means: a 2-page memo with measured equity-routing impact + measured quality delta. Bring this to mid-pilot review with the agency partner.

Phase 4 — Scale (post-pilot, 9/15 onward)

Goal: if pilot succeeds, expand to additional complaint categories and additional agencies. Stop being a research project; become infrastructure.

4a. Three-trade expansion (per the Framework section)

☐  Sidewalk repair (DOT): clone build-vendors.py with acd4-wkax + ckqw-hc7u datasets. Repoint the SoQL keyword filter to sidewalk/concrete.

☐  Tree pruning (DPR): clone with bdjm-n7q4 + hn5i-inap. ISA Certified Arborist filter.

☐  Lead paint abatement (HPD): clone with vq35-j9qm + EPA RRP firm registry. Add HPD ERP PQL flag.

☐  Each trade gets its own /trade/<name> page on the website with its own matrix and its own concentration story.

4b. EIN-based vendor identity (external)

☐  Stop relying on fuzzy name matching. Get PASSPort to expose EIN via API, OR scrape PASSPort Public quarterly to map license # → EIN.

☐  Re-run all joins on EIN. Drop the ~5% of fuzzy matches that were misidentifications.

4c. Drive-time, not haversine (Nischal, ~1 day)

☐  Replace haversine in scorer.js with Google Maps Distance Matrix API call on the top-20 candidates before final ranking.

☐  Cache results per (origin, vendor) pair — the same vendor's drive-time from a complaint address rarely changes.

4d. Citizen impact dashboard (joint)

☐  Public-facing /impact page showing aggregate "since launch" metrics: $$$ to M/WBE, by ethnicity, by borough, by month.

☐  Live data, not static. Auto-updates on every new dispatch.

☐  This is the asset for press, for the next microgrant, for the SF expansion pitch.

4e. SF expansion (the microgrant scope)

☐  Once NYC pilot is validated: clone the pipeline against DataSF 311 + DataSF M/WBE registry.

☐  SF equivalent of PPB Rule 3-08: SF Chapter 14B (LBE Ordinance). Different mechanics, same policy intent.

☐  Don't start this before NYC has 30+ real dispatches. Don't spread thin.

Decisions we need to make this week

Who pings Shukla's office Monday to confirm the 5/19 meeting and pre-share the methodology doc?

Database choice: Supabase (recommended) or Cloudflare D1? Decision deadline Fri 5/23.

Do we keep the demographic badges public-facing in the meantime, or make them dispatcher-only until legal review clears? Default: dispatcher-only for safety.

Pilot ask scope: one complaint category for one quarter, or open-ended commitment? Recommendation: ask for the narrowest, easiest yes first.

Sub-pilot fallback: if Shukla can't intro to a city agency by 5/26, do we pivot to NYU Wagner / Columbia SIPA / a civic-tech nonprofit (BetaNYC, Code for America) as a proxy validator? Decision deadline Fri 5/30.

Suggested owner split

| Workstream | Owner | Why |
| --- | --- | --- |
| Partnership outreach (Shukla → agency intro) | Nischal | Closer to the existing relationship |
| PPB 3-08 memo generator (PDF templating) | Mithran | Backend work, plays to systems strength |
| Mobile + accessibility polish | Nischal | Owns the current UI |
| Vendor portal | Mithran | Most net-new feature, backend-heavy |
| NYC.id SSO | Mithran | Auth/infra category |
| Email dispatch infrastructure | Nischal | Touches the demo flow Nischal already knows |
| Outcome feedback loop (mid-pilot) | Joint | Both need to see the data shape |

Kill criteria — when to stop

Honest stop conditions, so we don't pour energy into a project we should have stopped:

No agency partner committed by 6/30. Pivot to research-paper mode or shut down.

Legal review surfaces a blocker we can't cleanly mitigate (e.g. publishing demographic data is plainly illegal). Pivot to dispatcher-only mode.

Pilot launches but fewer than 10 dispatches happen in 90 days. Tool isn't being used; rethink before adding features.

Vendor complaints about misidentification reach 5% of total vendors surfaced. Trust is broken; we need EIN-based identity before continuing.

Set calendar reminders for each of these dates. Decide ahead of time what "kill" actually means: shut down, hand off to BetaNYC, paper-write-up, or pivot to the SF version using NYC as the prior art.

What to do in the next 48 hours

Sun 5/17: Both read the audit doc + this next-steps doc cover to cover. Pushback on anything you disagree with.

Sun 5/17 evening: 30-min sync to confirm owner split, decision deadlines, and the Shukla ask language.

Mon 5/18: Nischal pings Shukla's office to pre-share the methodology doc + confirm meeting time.

Mon 5/18: Mithran starts PPB 3-08 memo generator. Goal: prototype done by Tue meeting.

Mon 5/18 evening: Mobile/accessibility polish pass + favicon + meta tags.

Tue 5/19 morning: dry-run the full flow on Mithran's phone and Nischal's laptop. Have both. Have screenshots.

Tue 5/19 afternoon: Meeting. Lead with the institutional ask, demo the tool, hand over the docs.

— Nischal & Mithran